## Sheet1
PSP-Code	Vorgang	Dauer in Tagen	Vorgänger	AOB
M0	Projekt Initiierung	0 tage
INF-B	Projektmanagement	127 tage
INF-B-1	Steuerung & Controlling	125 tage	M0	NF
INF-B-2	Teamentwicklung	125 tage	M0	NF
INF-B-3	Risiko-/ Stakeholdermanagement	125 tage	M0	NF
INF-B-4	Qualitätsmanagement	125 tage	M0	NF
INF-B-5	Änderungsmanagement	125 tage	M0	NF
INF-B-6	Kommunikation	125 tage	M0	NF
INF-B-7	Projektabschlussmeeting	1 tag	INF-B-1,INF-B-2,INF-B-3,INF-B-4,INF-B-5,INF-B-6,M4	NF
M5	Projektende	0 tage	INF-B-7	NF
INF-C	Pre-Alpha-Phase	39 tage
INF-C-1	Kick-Off-Meeting	1 tag	M0	NF
INF-C-2	Scrum-Teams bilden	3 tage	INF-C-1	NF
INF-C-3	Sprint-Planning I	1 tag	INF-C-2	NF
INF-C-4	Softwareentwicklung I	14 tage	INF-C-3	NF
INF-C-5	Infrastrukturentwicklung I	14 tage	INF-C-4	AA
INF-C-6	Testentwicklung I	14 tage	INF-C-4	AA
INF-C-7	Sprint-Review I	1 tag	INF-C-4,INF-C-5,INF-C-6	NF
INF-C-8	Sprint-Retrospective I	1 tag	INF-C-7	NF
INF-C-9	Sprint-Planning II	1 tag	INF-C-8	NF
INF-C-10	Softwareentwicklung II	15 tage	INF-C-9	NF
INF-C-11	Infrastrukturentwicklung II	15 tage	INF-C-10	AA
INF-C-12	Testentwicklung II	15 tage	INF-C-10	AA
INF-C-13	Sprint-Review II	1 tag	INF-C-10,INF-C-11,INF-C-12	NF
INF-C-14	Sprint-Retrospective II	1 tag	INF-C-13	NF
INF-C-15	Learning	33 tage	INF-C-14	NF
INF-C-16	Einbindung Kundenfeedback	37 tage	INF-C-1	NF
INF-C-17	Interne Dokumentation	37 tage	INF-C-1	NF
M1	Softwareveröffentlichung im Git-Repository	0 tage	INF-C-14,INF-C-15,INF-C-16,INF-C-17	NF
INF-D	Alpha-Phase	23 tage
INF-D-1	Sprint-Planning III	1 tag	M1	NF
INF-D-2	Testentwicklung III	20 tage	INF-D-1	NF
INF-D-3	Softwareentwicklung III	20 tage	INF-D-2	AA
INF-D-4	Infrastrukturentwicklung III	20 tage	INF-D-2	AA
INF-D-5	Sprint-Review III	1 tag	INF-D-1,INF-D-2,INF-D-2	NF
INF-D-6	Sprint-Retrospective III	1 tag	INF-D-5	NF
INF-D-7	Learning	21 tage	INF-D-1	NF
INF-D-8	Einbindung Kundenfeedback	22 tage	M1	NF
INF-D-9	Interne Dokumentation	22 tage	M1	NF
M2	Softwareveröffentlichung auf dem Entwicklungsserver	0 tage	INF-D-6,INF-D-7,INF-D-8,INF-D-9	NF
INF-E	Beta-Phase	22 tage
INF-E-1	Sprint-Planning IV	1 tag	M2	NF
INF-E-2	Testentwicklung IV	19 tage	INF-E-1	NF
INF-E-3	Softwareentwicklung IV	19 tage	INF-E-2	AA
INF-E-4	Infrastrukturentwicklung IV	19 tage	INF-E-2	AA
INF-E-5	Sprint-Review IV	1 tag	INF-E-2,INF-E-3,INF-E-4	NF
INF-E-6	Sprint-Retrospective IV	1 tag	INF-E-5	NF
INF-E-7	Learning	20 tage	INF-E-1	NF
INF-E-8	Einbindung Kundenfeedback	21 tage	M2	NF
INF-E-9	Interne Dokumentation	21 tage	M2	NF
M3	Softwareveröffentlichung auf dem Produktivserver	0 tage	INF-E-6,INF-E-7,INF-E-8,INF-E-9	NF
INF-F	Continuous-Beta-Phase	42 tage
INF-F-1	Sprint-Planning V	1 tag	M3	NF
INF-F-2	Testentwicklung V	17 tage	INF-F-1	NF
INF-F-3	Softwareemtwicklung V	17 tage	INF-F-1	NF
INF-F-4	Infrastrukturentwicklung V	17 tage	INF-F-1	NF
INF-F-5	Sprint-Review V	1 tag	INF-F-2,INF-F-3,INF-F-4	NF
INF-F-6	Sprint-Retrospective V	1 tag	INF-F-4	NF
INF-F-7	Sprint-Planning VI	1 tag	INF-F-5	NF
INF-F-8	Testentwicklung VI	19 tage	INF-F-7	NF
INF-F-9	Softwareentwicklung VI	19 tage	INF-F-8	AA
INF-F-10	Infrastrukturentwicklung VI	19 tage	INF-F-8	AA
INF-F-11	Sprint-Review VI	1 tag	INF-F-8,INF-F-9,INF-F-10	NF
INF-F-12	Sprint-Retrospective VI	1 tag	INF-F-10	NF
INF-F-13	Learning	40 tage	INF-F-1	NF
INF-F-14	Einbindung Kundenfeedback	41 tage	M3	NF
INF-F-15	Interne Dokumentation	41 tage	M3	NF
M4	Continuous-Beta-Release-Veröffentlichung auf dem Produktivserver	0 tage	INF-F-12,INF-F-13,INF-F-14,INF-F-15	NF